## Sheet1
Week 1 | 2023-09-18 | Intro and Process Overview
Week 2 | 2023-09-25 | Project Ideas
Week 3 | 2023-10-02
Week 4 | 2023-10-09
Week 5 | 2023-10-16
Week 6 | 2023-10-23
Week 7 | 2023-10-30
Week 8 | 2023-11-06
Week 9 | 2023-11-13
Week 10 | 2023-11-20
Week 11 | 2023-11-27
Week 12 | 2023-12-04
Week 13 | 2023-12-11

## Sheet2
| 2023-09-18 | 2023-09-25 |  | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 |  | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 |  | 2024-03-25 | 2023-04-01
Initial Proposal |  |  | Proposal Submission | Proposal | Signed Off Proposal | [7 empty] | Interim Submission | [16 empty] | Final Submission
Requirements Gathering |  |  |  | Requirements Document
Background Research |  |  |  |  | Chapter 2 - Background Research
Design of Evaluation | [6 empty] | Chapter 3 - Test Plan
Initial Design | [8 empty] | Chapter 3 - Design
Prototype / Proof-of-Concept | [10 empty] | Proof of Concept
Prototype Write-Up | [10 empty] | Chapter 4 - Prototype
Interim Report | [11 empty] | Interim Submission
Interim Demo | [13 empty] | 2023-12-04: Demo and Presentation
Final Design | [13 empty] | 2024-01-15: Chapter 3 - Design (final)
Implementation Process | [13 empty] | 2024-02-19: System Artificat
Implementation Write-up | [13 empty] | 2024-02-05: New level designs; 2024-02-26: Chapter 4 - System Development
Project Evaluation | [13 empty] | 2024-02-12: Debugging; 2024-02-26: Functional testing; 2024-03-04: Chapter 5 - Evaluation
Dissertation Document | [13 empty] | 2024-03-18: Dissertation (final)
Final Demonstration | [30 empty] | Demo and Presentation